## Model Development
Item | Responsible | Due Date
Extract, transform and group datasets by zipcode and month | Juan David | 19/03/2023
Filter and clean data, excluding non residential zip codes and save in a new file | Jane Bugai | 2023-03-24
Create a synthetic data with builiding zip codes | Jane Bugai | 2023-03-24
Plot and understand trend, seasonality and distribution of the price and complaints time series | all
Develop and experiment with different approaches for the general lineal model | all
Try non-linear options (log-lin, lin-log, log-log, polynomial) | all
Develop and experiment with different approaches for the gradient (MoM change) lineal model | all
Try non-linear options (log-lin, lin-log, log-log, polynomial) | all
Develop and experiment with different approaches for the N+1 gradient predictive (MoM change) lineal model | all

## Deliverables
Phase | Project Deliverable | Requirement | Responsible | Due Date (D/M/Y)
2 | Proposal Video Presentation | work on exploring datasets, data cleaning, and model building | all
2 | Proposal Video Presentation | update the video presentation ppt and script
2 | Proposal Video Presentation | check that we met presentation requirements: • 4-5 minutes long? • all team members listed? • necessary background info/framing of problem? • planned approach? • initial hypotheses? • what models are used? • progress update: unexpected problems/challenges, interesting findings • reviewed and discussed 2-3 research articles/papers/Kaggle kernels/etc. related to your problem statement? • visuals AND slides included? • References listed?
2 | Proposal Video Presentation | create a 4-5 minute long video presentation using the script & ppt.
2 | Proposal Video Presentation | upload the video as an unlisted YouTube video
2 | Proposal Video Presentation | name the video using the format: "[Project Name] Team10 Proposal Video Presentation"
2 | Proposal Video Presentation | add a description to the video with a brief overview of the 1) video, 2) your team, 3) your team number, and 4) project.
2 | Proposal Video Presentation | double-check that the URL works, visit that URL using a separate web browser that has been fully logged out of Google services (e.g., all cache cleared, use “Incognito” mode in Chrome, etc.)
2 | Proposal Video Presentation | submit unlisted YouTube video URL in Canvas. | Juan | 26/3/23
3 | Progress Report | check that requirements are met for a formal progress report/"academic-like" paper providing a detailed description of what we've done and includes: • 3-5 pages long (from syllabus...double check that this doesn't change) • a clear explanation and proper background? • novelties of our approach are described? • necessary background info/framing of the problem? • planned approach? • update on data cleaning progress? • anything unexpected? • literature survey with at least 2-3 sources? • references listed? • key visuals included?
Progress Report
Progress Report
Progress Report
| Progress Report | submit pdf of report using the following format: "team10progressreport.pdf" | Juan | 2023-02-04
4 | Fnal Video Presentation
4 | Final Report, Data, & Code
5 | Out-of-Group Final Video Peer Review
5 | Within-Group Final Peer Reivew